## sakura creative
Sakura Creative
Rules and start-up
Name | Subitems | Person | Status | Date | Epic
Rules |  |  | All done! | 2024-09-09
Roles |  |  | All done! | 2024-09-09
Teamname | Brainstorm |  | All done! | 2024-09-09
Subitems | Name | Owner | Status | Date | Description
| Brainstorm |  | Not started
Contract |  |  | All done! | 2024-09-11
2024-09-09 tot 2024-09-11
Backlog
Name | Subitems | Person | Status | Date | Epic
Sprint 1
Name | Subitems | Person | Status | Date | Epic
Logo | Sketches, Final design | Sanne Reniers | All done! | 2024-09-16 | Branding
Subitems | Name | Owner | Status | Date | Description
| Sketches |  | All done!
| Final design |  | All done!
Brand book | Low fidelty, High fidelty, Mock-ups | Sanne Reniers, Furkan Smail, Safa Hassan | All done! | 2024-09-25 | Branding
Subitems | Name | Owner | Status | Date | Description
| Low fidelty | Sanne Reniers, Furkan Smail | All done! | 2024-09-18 | Feedback, high fidelty
| High fidelty | Sanne Reniers, Furkan Smail | All done! | 2024-09-23
| Mock-ups | Safa Hassan | All done! | 2024-09-18 | Business card, T-shirt, Cap, Sticker
Brand identity |  | Furkan Smail, Artem Arzumanian, Quinn Lutters | All done! | 2024-09-16 | Branding
Website prototype | Inspiration, Low fidelty, High fidelty, Sketch, Mid fidelity | Artem Arzumanian, Hakan Coban | All done! | 2024-09-20 | Client Product
Subitems | Name | Owner | Status | Date | Description
| Sketch | Artem Arzumanian | All done! | 2024-09-16
| Inspiration | Hakan Coban | All done! | 2024-09-17
| Low fidelty | Artem Arzumanian | All done! | 2024-09-19
| Mid fidelity | Artem Arzumanian | All done! | 2024-09-20 | Ask feedback
| High fidelty | Artem Arzumanian, Sanne Reniers | All done! | 2024-09-23
Development Website | Hero section, Team section, Value section, Full website responsivness, 3D model and Brand book incorporation | Hakan Coban, Artem Arzumanian | Working on it | 2024-09-25 | Client Product
Subitems | Name | Owner | Status | Date | Description
| Hero section | Artem Arzumanian | All done! | 2024-09-24
| Team section | Artem Arzumanian | All done! | 2024-09-25
| Value section | Hakan Coban | Working on it
| Full website responsivness | Artem Arzumanian, Hakan Coban | Not started
| 3D model and Brand book incorporation |  | Not started
3D Model | Sketch, Draft of model, Finished model | Quinn Lutters | All done! | 2024-09-25 | Branding
Subitems | Name | Owner | Status | Date | Description
| Sketch | Quinn Lutters | All done! | 2024-09-17
| Draft of model |  | All done! | 2024-09-18
| Finished model |  | All done! | 2024-09-23
Motivation letter | Drafting, Finished letter | Quinn Lutters, Safa Hassan | Working on it | 2024-09-25 | Client Product
Subitems | Name | Owner | Status | Date | Description
| Drafting | Safa Hassan | Working on it | 2024-09-23 | Keypoints from brand identity, draft for the first presentation (mach8)
| Finished letter |  | Not started | 2024-09-25
Presentation | Halfway presentation, Final presentation | Sanne Reniers, Furkan Smail, Quinn Lutters, Artem Arzumanian | Working on it | 2024-09-17 | Presentation
Subitems | Name | Owner | Status | Date | Description
| Halfway presentation |  | All done! | 2024-09-17 | Look at figma presenation and canva
| Final presentation |  | Not started | 2024-09-30
Sprint retrospective |  |  | All done! |  | Sprint
2024-09-16 tot 2024-09-25